## Sheet1
E = Erika, Ky = Kylie, Ke = Kendall, P = Pamela |  |  | May |  |  |  | May | [6 empty] | May | [6 empty] | May | [6 empty] | May-June | [6 empty] | June | [6 empty] | June | [6 empty] | June | [6 empty] | June-July | [6 empty] | July | [6 empty] | July | [6 empty] | July | [6 empty] | July | [6 empty] | July-Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug | [6 empty] | Aug-Sept | [6 empty] | Sept | [6 empty] | Sept | [6 empty] | Sept | [6 empty] | Sept | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct | [6 empty] | Oct-Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov | [6 empty] | Nov-Dec | [6 empty] | Dec | [6 empty] | Dec
TASK | START | END | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Software Development | 2023-05-03 | 2023-12-01
Requirements Spec. & Design
Requirements Specification | 2023-05-03 | 2023-05-10 | E, Ky, Ke, P
Engine Architecture Design | 2023-05-10 | 2023-06-17 | [7 empty] | E
Interface Layout & Design | 2023-05-17 | 2023-07-22 | [14 empty] | Ky
Interface Task Breakdown
Wireframing | 2023-05-17 | 2023-07-12 | [14 empty] | Ky
New Project Wizard | 2023-05-24 | 2023-07-05 | [21 empty] | Ky
Database (DB) Construction | 2023-05-17 | 2023-07-05 | [14 empty] | Ky
Database Communication with Interface | 2023-05-17 | 2023-07-05 | [21 empty] | Ky
Exporting PDF File Ability | 2023-05-24 | 2023-07-05
Engine Task Breakdown
Object Handler | 2023-05-17 | 2023-07-12 | [14 empty] | E
Text Handler | 2023-05-24 | 2023-07-12 | [21 empty] | E
Logic Handler | 2023-05-24 | 2023-07-12 | [21 empty] | E
Attribute Handling | 2023-05-31 | 2023-07-12 | [28 empty] | E
Unit Pathing | 2023-05-24 | 2023-07-12 | [21 empty] | E
File I/O Parser | 2023-05-24 | 2023-07-12 | [21 empty] | E
Help Task Breakdown
Interface Help | 2023-07-05 | 2023-07-26 | [63 empty] | Ke
Engine Help | 2023-07-05 | 2023-07-26 | [63 empty] | Ke
Database Help | 2023-07-05 | 2023-07-26 | [63 empty] | Ke
FAQ | 2023-07-05 | 2023-07-26 | [63 empty] | Ke
Manual | 2023-07-26 | 2023-08-09 | [84 empty] | Ke
Test Task Breakdown
Unit Testing | 2023-05-17 | 2023-07-12 | [14 empty] | P
Integration & Database Testing | 2023-07-12 | 2023-08-12 | [21 empty] | P | [48 empty] | P
Validation Testing | 2023-05-31 | 2023-08-19 | [28 empty] | P
Performance Testing | 2023-08-06 | 30-Sept | [35 empty] | P | [59 empty] | P
Cloud Based Testing | 2023-08-16 | 23-Sept | [105 empty] | P
Documentation
Use Case Document | 2023-05-10 | 2023-06-07 | [7 empty] | E, Ky, Ke, P
Software Requirements | 2023-05-10 | 2023-07-12 | [7 empty] | E, Ky, Ke, P
Software Quality Assurance Plan | 2023-05-10 | 2023-07-12 | [7 empty] | E, Ky, Ke, P
Risk Management Plan | 2023-05-17 | 2023-06-28 | [14 empty] | E, Ky, Ke, P
Software Configuration Mgmt | 2023-06-14 | 2023-08-09 | [42 empty] | E, Ky, Ke, P
Project Plan | 2023-05-10 | 2023-06-28 | [7 empty] | E, Ky, Ke, P
Prototype | 2023-07-12 | 2023-08-22 | [70 empty] | E, Ky, Ke, P | [156 empty] | #NAME?
Senior Design Abstract | 2023-08-30 | 2023-12-16 | [119 empty] | E, Ky, Ke, P
Electronic Poster | 2023-08-30 | 2023-12-16 | [40 empty] | Ky | [78 empty] | E, Ky, Ke, P
Test Plan | 2023-08-30 | 2023-10-30 | [119 empty] | E, Ky, Ke, P
Final Demo | 2023-08-30 | 2023-12-14 | [40 empty] | Ky | [78 empty] | E, Ky, Ke, P
Post Mortem | 2023-08-30 | 2023-12-11 | [40 empty] | E | [78 empty] | E, Ky, Ke, P
Client Documentation
One-Note | 2023-06-12 | 2023-06-15 | [40 empty] | Ky
ERD Diagram | 2023-06-12 | 2023-06-16 | [40 empty] | E
Data Model | 2023-06-12 | 2023-06-17 | [40 empty] | E